## Sheet1
Name | Due date | Description | Progress | Status
Presentation slide deck | Sun, Dec 15 | 7-15 slides | lol fuck | 0
Presentation recording | Sun, Dec 15 | intro, research question, high level data source overview, how data sources were combined, problems overcome, prelim results and discussion of value | lol shit | 0
Conference talk proposal | Sun, Dec 15 | Submission for a PyCon 2019 talk; speaker bio, talk title, description, who & why, outline, additional notes | mostly done! Just need to write talk description | 1
Intermediate datasets | Tues, Dec 17 | Cleaned versions of datasets used to produce the final dataset; used in Jupyter Notebook | For each dataset, the records that I'll use to form the final dataset are clean and ready for extraction. Each dataset also has its own versioning folder with different versions at fairly consistent stages. | 2
Processing code | Tues, Dec 17 | Commented and documented code for all data gathering you did using code. Any hand created files should have detailed descriptions of their creation. | Used code for ESTC and gutenberg and added comments | 2
Notes on hand-editing | Tues, Dec 17 | For each dataset documentation file: notes on any hand-editing conducted | added to "cleaning assessment" sections of individual dataset documentation files | 2
Final dataset file | Tues, Dec 17 | CSV file containing final data; produced with Jupyter Notebook | it exists! final_dataset.csv | 2
Github Repo | Tues, Dec 17 | contains everything above. If you have data that’s too big to be stored in github, you’ll need to have it hosted in a box folder or something. | updating as I go | 2
Dataset documentation files | Tues, Dec 17 | in "data-documentation-files", .md files | pretty sure this is done! | 2
Jupyter Notebook | Tues, Dec 17 | A notebook with code to reproducibly create your final data file from your intermediate data files, with comments and narrative, suitable for a tutorial or demonstration. I should be able to delete your final data fiile and recreate it based just off your intermediate data files and the code in this notebook. | green light from elizabeth! it's done! | 2
Manifest file | Tues, Dec 17 | Shows which files contain all the checklist elements | MANIFEST.md (still missing file name identifiers for resume entry, summary slide, assessment report) | 1
Summary slide | Tues, Dec 17 | single summary slide of your project that can be used next semester as an example for other students | lol why | 0
Assessment report | Tues, Dec 17 | PDF showing some initial analysis of your data. Max 2 pages. Show me if this dataset was worth pursuing and what research questions you can ask of it. Imagine this report will be given to a data science lead who asked you to complete this exploratory project. Write for that audience. | lol fuck | 0
Résumé entry | Tues, Dec 17 | either submit an updated resume with this element highlighted or submit the text extract as a PDF | Just submit the text extract; I don't have time to rewrite my whole resume | 0