## Weeks
NAME | AUTHORITY | DATASET SOURCE | WEEK 1 |  |  |  | WEEK 2 |  |  |  | WEEK 3 (September 9 - September 15) |  |  |  | WEEK 4 (September 16 - September 22) |  |  |  | WEEK 5 (September 23 - September 29) |  |  |  | WEEK 6 (September 30 - October 6) |  |  |  | WEEK 7 (October 7 - October 13) |  |  |  | WEEK 8 (October 14 - October 20) |  |  |  | WEEK 9 (October 21 - October 27) |  |  |  | WEEK 10 (October 28 - November 3) |  |  |  | WEEK 11 (November 4 - November 10) |  |  |  | WEEK 12 (November 11 - November 17) |  |  |  | WEEK 13 (November 18 - November 24 |  |  |  | WEEK 14 (November 25 - December 1) |  |  |  | WEEK 15 (December 2 - December 8) |  |  |  | WEEK 16 (December 9 - December 15)
|  |  | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status
Elizabeth Assignment | [10 empty] | Dataset inventory and reviews |  | 2019-09-15 | o | Recruiter and interviewer pitch |  | 2019-09-22 | o | Final project proposal |  | 2019-09-29 | o | [8 empty] | Data management and project management plans |  | 2019-10-20 | o |  |  |  |  | Data documentation assessment |  | 2019-11-03 | o | Final dataset design plan |  | 2019-11-10 | x | Midpoint checkin materials |  | 2019-11-17 | x | Reproducible notebook draft |  | 2019-11-24 | x |  |  |  |  | Conference talk proposal |  | 2019-12-08 | x | Final project recording, all deliverables |  | 2019-12-15 | x
Project deliverables | [54 empty] | Work on conference talk proposal |  | 2019-12-08 | x | Wrap up conference talk proposal |  | 2019-12-08 | x | Record final presentation |  | 2019-12-15 | x
[55 empty] | Start organizing final deliverables |  | 2019-12-15 | x | Script final presentation |  | 2019-12-15 | x | Compile final deliverables |  | 2019-12-15 | x
Standardization Schema | [34 empty] | Write standardization schema | standardization-schema.? (csv? doc?) | 2019-10-27 | o
Final Dataset | [46 empty] | Troubleshoot reformatting datasets / data mashup process |  | 2019-11-24 | x | Combine datasets together | Jupyter notebook, final-dataset.csv | 2019-11-24 | x | Develop analysis and create visualizations | open-data-mashups-viz.docx ; open-data-mashups-viz.xlsx ; open-data-mashups-viz.ai | 2019-12-01 | x
eebo | ProQuest | https://search.proquest.com/eebo/index | [12 empty] | Choose dataset (original EEBO or ProQuest) | https://search.proquest.com/eebo/index | 2019-09-21 | o |  |  |  |  | Manually extract authors in year chunks; combine in one column | eebo_dataset_raw.xlsx ; eebo_dataset_combined.csv | 2019-10-06 | o | [12 empty] | Reformat dataset according to data standardization schema | .py ; eebo_dataset_standardized.csv | 2019-11-03 | o
[23 empty] | Consolidate authors (https://stackoverflow.com/questions/54593232/how-do-i-combine-rows-in-open-refine) | eebo_dataset_cleaned.xlsx | 2019-10-06 | o
estc | HathiTrust | https://babel.hathitrust.org/cgi/mb?a=listis&c=247770968 | [12 empty] | Choose dataset (original ESTC or HathiTrust) | https://babel.hathitrust.org/cgi/mb?a=listis&c=247770968 | 2019-09-21 | o | [12 empty] | Extract authors from JSON file using Python | estc_extraction.py ; estc_dataset.csv | 2019-10-20 | o |  |  |  |  | Reformat dataset according to data standardization schema | .py ; estc_dataset_standardized.csv | 2019-11-03 | x
[31 empty] | Consolidate authors | estc_dataset_cleaned.xlsx | 2019-10-20 | o
open-syllabus | Open Syllabus Project | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature&countries=US | [12 empty] | Set Explorer parameters | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature&countries=US | 2019-09-21 | o | Extract authors using XPATH | open-syllabus_dataset.xlsx | 2019-10-06 | o | [24 empty] | Reformat dataset according to data standardization schema | .py ; open-syllabus_dataset_standardized.csv | 2019-11-17 | x
|  | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature | [13 empty] | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature
ota | Oxford Text Archive | https://ota.ox.ac.uk/catalogue/index.html | [12 empty] | Use "View Source" to create dataset file | view-source_ota.ox.ac.uk_catalogue_index.html | 2019-09-21 | o |  |  |  |  | Extract authors from HTML file using Python (reformat HTML file as program gets stuck on inconsistencies) | ota_extraction.py ; ota_source_edited.html ; ota_authors_dataset.csv | 2019-10-06 | o | [16 empty] | Reformat dataset according to data standardization schema | .py ; ota_dataset_standardized.csv | 2019-11-10 | x
[23 empty] | Consolidate authors | ota_dataset_cleaned.xlsx | 2019-10-06 | o
project-gutenberg | Project Gutenberg | http://gutenberg.pglaf.org/cache/generated/feeds | [12 empty] | Download catalog RDF file | project-gutenberg_catalog.rdf | 2019-09-21 | o |  |  |  |  | Extract authors from RDF file using Python | project-gutenberg_extraction.py ; project-gutenberg_dataset.csv | 2019-10-06 | o
[23 empty] | Consolidate authors | project-gutenberg_dataset_cleaned.csv | 2019-10-06 | o
project-gutenberg-2 | Project Gutenberg | http://gutenberg.pglaf.org/cache/generated/feeds | [24 empty] | Download catalog TAR file | rdf-files.tar | 2019-10-13 | o |  |  |  |  | Consolidate authors | project-gutenberg-2_dataset_cleaned.csv | 2019-10-27 | o |  |  |  |  | Reformat dataset according to data standardization schema | .py ; project-gutenberg_dataset_standardized.csv | 2019-11-10 | x
wikidata | Wikidata | https://query.wikidata.org

## Stages
NAME | AUTHORITY | DATASET SOURCE | STAGE 1 - dataset selection |  |  |  | STAGE 2 - data extraction |  |  |  | STAGE 3 - cleaning and count consolidation |  |  |  | STAGE 4 - standardization schema |  |  |  | STAGE 5 - reformatting and standardizing datasets |  |  |  | STAGE 6 - data mashup |  |  |  | STAGE 7 - analysis and visualization
|  |  | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status | Description | Product | Due Date | Status
Standardization Schema | [14 empty] | Write standardization schema | standardization-schema.? (csv? doc?) | 2019-10-27 | x
Final Dataset | [22 empty] | Combine datasets together | Jupyter notebook, final-dataset.csv | 2019-11-24 | x | Develop analysis and create visualizations | open-data-mashups-viz.docx ; open-data-mashups-viz.xlsx ; open-data-mashups-viz.ai | 2019-12-01 | x
eebo | ProQuest | https://search.proquest.com/eebo/index | Choose dataset (original EEBO or ProQuest) | https://search.proquest.com/eebo/index | 2019-09-21 | o | Manually extract authors in year chunks; combine in one column | eebo_dataset_raw.xlsx ; eebo_dataset_combined.csv | 2019-10-06 | o | Consolidate authors (https://stackoverflow.com/questions/54593232/how-do-i-combine-rows-in-open-refine) | eebo_dataset_cleaned.xlsx | 2019-10-06 | o |  |  |  |  | Reformat dataset according to data standardization schema | .py ; eebo_dataset_standardized.csv | 2019-11-03 | x
estc | HathiTrust | https://babel.hathitrust.org/cgi/mb?a=listis&c=247770968 | Choose dataset (original ESTC or HathiTrust) | https://babel.hathitrust.org/cgi/mb?a=listis&c=247770968 | 2019-09-21 | o | Extract authors from JSON file using Python | estc_extraction.py ; estc_dataset.csv | 2019-10-20 | o | Consolidate authors | estc_dataset_cleaned.xlsx | 2019-10-20 | o |  |  |  |  | Reformat dataset according to data standardization schema | .py ; estc_dataset_standardized.csv | 2019-11-03 | x
open-syllabus | Open Syllabus Project | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature&countries=US | Set Explorer parameters | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature&countries=US | 2019-09-21 | o | Extract authors using XPATH | open-syllabus_dataset.xlsx | 2019-10-06 | o | [8 empty] | Reformat dataset according to data standardization schema | .py ; open-syllabus_dataset_standardized.csv | 2019-11-10 | x
|  | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature |  | https://opensyllabus.org/results-list/authors?size=5000&fields=English%20Literature
ota | Oxford Text Archive | https://ota.ox.ac.uk/catalogue/index.html | Use "View Source" to create dataset file | view-source_ota.ox.ac.uk_catalogue_index.html | 2019-09-21 | o | Extract authors from HTML file using Python (reformat HTML file as program gets stuck on inconsistencies) | ota_extraction.py ; ota_source_edited.html ; ota_authors_dataset.csv | 2019-10-06 | o | Consolidate authors | ota_dataset_cleaned.xlsx | 2019-10-06 | o |  |  |  |  | Reformat dataset according to data standardization schema | .py ; ota_dataset_standardized.csv | 2019-11-03 | x
project-gutenberg | Project Gutenberg | http://gutenberg.pglaf.org/cache/generated/feeds | Download catalog RDF file | project-gutenberg_catalog.rdf | 2019-09-21 | o | Extract authors from RDF file using Python | project-gutenberg_extraction.py ; project-gutenberg_dataset.csv | 2019-10-06 | o | Consolidate authors | project-gutenberg_dataset_cleaned.csv | 2019-10-06 | o
project-gutenberg-2 | Project Gutenberg | http://gutenberg.pglaf.org/cache/generated/feeds | Download catalog TAR file | rdf-files.tar | 2019-10-13 | o | Extract authors from RDF files using Python | project-gutenberg-2_extract.py ; project-gutenberg-2_dataset.csv | 2019-10-27 | x | Consolidate authors | project-gutenberg-2_dataset_cleaned.csv | 2019-10-27 | x |  |  |  |  | Reformat dataset according to data standardization schema | .py ; project-gutenberg_dataset_standardized.csv | 2019-11-17 | x
wikidata | Wikidata | https://query.wikidata.org